## NEWTOWN
EASTERN CORRIDOR SEGMENTS II-III CONCEPT DEVELOPMENT SUMMARY
NEWTOWN FOCUS AREA
REV. MAY 16, 2018
Theme | Needs | Evaluation Criteria | Concepts | [12 empty] | Recommendation | Advisory Committee Feedback
|  |  | Identifier | Description | Meets Primary Need(s)? | Meets Secondary Need(s)? | Safety | Traffic Operations | Constructability Issues | Construction Cost | R/W Impacts | Environmental / Community Impacts | Support and/or Facilitate Multi-Modal | Improve Regional Connectivity | Improve Local Access | (as of May 16 Advisory Committee meeting) | COMMENTS | REVIEWER
SR 32 Corridor | Primary P1) Address westbound AM eastbound PM peak-hour delays. P2) Address capacity issues and long queues at the Church/Main intersection. P3) Address capacity issues and long queues at the Round Bottom intersection. Secondary S1) Address deficient sight distance at Round Bottom intersection. S2) Support access to future transit connections. | • Provide more efficient travel patterns and destination linkages. • Augment capacity and provide congestion relief. • Reduce travel times and delays. • Improve vehicular, bicycle, and pedestrian safety. • Improve regional connectivity and accessibility to regional destinations including the airport, downtown Cincinnati, and Kenwood. • Support and facilitate bus, rail, and TSM investments. • Support existing and planned land use. • Maintain local character of Village and small town feel. • Minimize environmental and community impacts. | STS | Improve signal timing. | P1, P4, P5 | [10 empty] | Advance
|  |  | I-6a | Lengthen turn lanes at the Church/Main intersection and add EB/WB through lanes on SR 32 if it can be accomplished with little to no additional right-of-way. | P1, P2 | [10 empty] | Advance with I-5a or I-5b.
|  |  | I-6b-1 | Install roundabout at Church/Main intersection. Add EB/WB through lanes on SR 32 if it can be accomplished with little to no additional right-of-way. | P1, P2, P4 | [10 empty] | No further study
|  |  | I-6b-2 | Install offset roundabout at Church/Main intersection. Add EB/WB through lanes on SR 32 if it can be accomplished with little to no additional right-of-way. | P1, P2, P4 | [10 empty] | No further study
|  |  | I-5a | Increase left turn lane storage along SR 32, add EB lane, and add dual SB left turn lanes at Round Bottom intersection. Add EB/WB through lanes on SR 32 if it can be accomplished with little to no additional right-of-way. | P1, P3 | [10 empty] | Advance
|  |  | I-5b-1 | Install a roundabout at Round Bottom intersection. Center on fountain location. | P1, P3, P4 | S1 | [9 empty] | No further study
|  |  | I-5b-2 | Install a roundabout at Round Bottom intersection. Relocate fountain. | P1, P3, P4 | S1
|  |  | I-5c | Address sight distance deficiency at Round Bottom intersection by extending culvert in order to modify fence. |  | S1 | [9 empty] | Secondary need to be addressed with other alternatives.
|  |  | STS | Signal improvements such as fiber interconnect, detection, “responsive” smart signals. | [11 empty] | Determine need after implementation of signal timing improvements.
Connection between SR 32 and US 50 Corridors | Primary P4) Address congestion. P5) Address capacity issues for NB left turn movement and EB approach at Round Bottom/Valley intersection. P6) Address northbound AM and southbound PM peak-hour delays. P7) Address capacity issues for SB left-turn movement at Church/Valley intersection. Secondary S3) Support access to future transit connections. S4) Correct deficient roadway curve near Natorp's Nursery. S5) Address roadway grades at railroad crossing. | • Provide more efficient travel patterns and destination linkages. • Augment capacity and provide congestion relief. • Reduce travel times and delays. • Improve vehicular, bicycle, and pedestrian safety. • Improve regional connectivity and accessibility to regional destinations including the airport, downtown Cincinnati, and Kenwood. • Support and facilitate bus, rail, and TSM investments. • Support existing and planned land use. • Maintain local character of Village and small town feel. • Minimize environmental and community impacts. | STS | Improve signal timing. | P1, P4, P5 | [10 empty] | Advance
|  |  | I-8a | Extend NB left turn lane, extend EB right turn lane, and at Round Bottom/Valley intersection. | P4, P5, P6 | [10 empty] | Advance
|  |  | I-8b | Install roundabout at Round Bottom/Valley intersection. | P4, P5, P6 | [10 empty] | Advance
|  |  | I-10a | Install five section head for WB right turn movement at Church/Valley intersection. | P4 | [10 empty] | Advance
|  |  | I-10b | Extend SB left turn lane at the Church/Valley intersection. | P4, P6, P7 | [10 empty] | Defer until analysis is completed
|  |  | I-10c | Install roundabout at Church/Valley intersection. | P4 | [10 empty] | Advance if roundabout is shifted to NW.
|  |  | I-10d | Install deferred left at Church/Valley intersection. | P4 | [10 empty] | No further study
|  |  | Church-1 | Adjust grade at railroad crossing on Church St |  | S5 | [9 empty] | Advance
Bicycle and Pedestrian | Primary P8) Address pedestrian connectivity to east corp. limit. Secondary S6) Enhance bicycle connectivity on Round Bottom Rd. S7) Enhance bicycle connectivity on Church St. S8) Address bicycle connectivity on SR 32 from west corp. line to Little Dry Run. | • Provide more efficient travel patterns and destination linkages. • Improve vehicular, bicycle, and pedestrian safety. • Improve regional connectivity to existing and planned bike/ped facilities. • Support existing and planned land use. • Maintain local character of Village and small town feel. • Maintain and enhance walkability within the Village. • Minimize environmental and community impacts. | 32-7 | Extend sidewalk to east corp. limit. | P8 | S8 | [9 empty] | Advance
|  |  | RB-1 | Add shared use path on Round Bottom Rd. east of Valley. |  | S6 | [9 empty] | Advance
|  |  | RB-2 | Add sidewalk on Round Bottom Rd. between SR 32 and Valley. |  | S6 | [9 empty] | Advance
|  |  | RB-3 | Connect park at Lake Barber with Little Miami Trail with sidewalk or bike path. Share corridor with connection to Riverside Park. |  | S6 | [9 empty] | Advance